## June
Status | Event ID | IFOA Region | State Forest | Compartment | POEO Schedule/Non-scheduled | EPL Licensed/Unlicensed | Nature of Operation | Silviculture | Intensity | Net Harvest Area (ha) | Estimated Yield (m³) | Dates (DD-MMM-YY) | [9 empty] | Slope Class (percentage of compartment - total must add up to 100) |  |  |  |  | Inherent Hazard Level | Roads - length in metres |  |  | Drainge Feature Crossings (No. of:) |  | Unmmaped Drainge Line Harvesting | TSL Schedule 6 (No. of)
[12 empty] | Plan Approved | Operation Proposed | Operation Commenced | Operation Suspended | Operation Recommenced | Operation Completed | EPL Commencement | EPL Temporarily Ceased | EPL Recommenced | EPL Final Ceased | <10° | 11-20° | 21-25° | 26-30° | 31°+ |  | New Road to be Constructed | Road with Grade >10% | Road on Slopes >30° | New Crossings | Existing Crossings to be used |  | FCNSW Mgr. Approval | EPA Approval
C | 126315 | SC | Benandarah | 114 | Non-scheduled | Unlicensed | Both | STS <50% | M | 175 | 4750 | 2018-05-04 | 2018-05-01 | 2018-05-11 | [7 empty] | 56 | 41 | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | Yes | 2 | 0
C | 126316 | SC | Benandarah | 116 | Non-scheduled | Unlicensed | Both | STS <50% | M | 160 | 5250 | 2018-05-04 | 2018-05-01 | 2018-05-11 | [7 empty] | 46 | 46 | 7 | 1 | 0 | 2 | 0 | 40 | 0 | 0 | 0 | Yes | 0 | 0
C | 126346 | SC | Bodalla | 3012 | Non-scheduled | Unlicensed | Both | STS <50% | H | 159 | 5300 | 2018-05-11 | 2018-04-01 | 2018-05-22 | [7 empty] | 70 | 27 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 1 | Yes | 0 | 0
C | 22297 | SC | Tallaganda | 2399 | Non-scheduled | Unlicensed | Both | STS <50% | M | 246 | 9618 | 2016-09-13 | 2016-09-01 | 2016-11-10 | 2017-02-28 | 2017-07-17 | [5 empty] | 32 | 55.5 | 10.6 | 2.3 | 0 | 2 | 100 | 0 | 0 | 0 | 9 | Yes | 0 | 0
C | 126321 | SC | Tallaganda | 2436 | Non-scheduled | Unlicensed | Both | STS <50% | M | 15 | 570 | 2018-02-06 | 2018-02-01 | 2018-02-07 | [7 empty] | 54 | 36 | 8 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | Yes | 0 | 0
C | 126319 | SC | Tallaganda | 2437 | Non-scheduled | Unlicensed | Both | STS <50% | M | 175 | 7280 | 2018-02-06 | 2018-02-01 | 2018-02-07 | [7 empty] | 62 | 34 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | Yes | 0 | 0
C | 126320 | SC | Tallaganda | 2438 | Non-scheduled | Unlicensed | Both | STS <50% | M | 161 | 1900 | 2018-02-06 | 2018-02-01 | 2018-02-07 | [7 empty] | 52 | 34 | 12 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 6 | Yes | 0 | 0
C | 126318 | SC | Flat Rock | 37 | Non-scheduled | Unlicensed | Both | STS <50% | H | 215 | 9800 | 2018-01-29 | 2018-02-01 | 2018-02-22 | [7 empty] | 62 | 35 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
C | 126261 | SC | Mogo | 144 | Non-scheduled | Unlicensed | Both | STS <50% | H | 183 | 10552 | 2018-02-16 | 2018-02-01 | 2018-03-07 | [7 empty] | 35 | 59 | 5 | 1 | 0 | 2 | 0 | 70 | 0 | 0 | 0 | Yes | 0 | 0
C | 126262 | SC | Mogo | 145 | Non-scheduled | Unlicensed | Both | STS <50% | H | 97 | 7835 | 2018-02-16 | 2018-02-01 | 2018-03-07 | [7 empty] | 33 | 63 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
C | 21861 | SC | Badja | 2023 | Non-scheduled | Licensed | Both | STS <50% | L | 250 | 4000 | 2015-04-02 | 2015-04-01 | 2015-04-16 | 2016-10-04 | 2018-03-09 | [5 empty] | 28 | 55 | 13 | 3 | 1 | 2 | 550 | 110 | 0 | 4 | 4 | No | 1 | 0
D | 126275 | SC | Boyne | 103 | Non-scheduled | Unlicensed | Both | STS <50% | M | 295 | 9960 | 2017-09-01 | 2017-09-01 | 2017-09-10 |  |  | 2018-05-09 |  |  |  |  | 39 | 52 | 7 | 2 | 0 | 2 | 0 | 89 | 0 | 0 | 0 | No | 0 | 0
D | 126324 | SC | Bodalla | 3023 | Non-scheduled | Unlicensed | Both | STS >50% | H | 100 | 6450 | 2018-03-12 | 2018-02-01 | 2018-03-15 |  |  | 2018-05-22 |  |  |  |  | 29 | 53 | 14 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 122199 | SC | Buckenbowra | 529 | Non-scheduled | Unlicensed | Both | STS <50% | M | 32 | 1200 | 2017-09-07 | 2017-09-01 | 2017-09-14 |  |  | 2018-03-12 |  |  |  |  | 26 | 65 | 8 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | No | 0 | 0
D | 122200 | SC | Buckenbowra | 530 | Non-scheduled | Unlicensed | Both | STS <50% | M | 156 | 5800 | 2017-09-07 | 2017-09-01 | 2017-09-14 |  |  | 2018-03-12 |  |  |  |  | 31 | 51 | 13 | 4 | 1 | 2 | 350 | 80 | 0 | 3 | 3 | No | 2 | 0
D | 122201 | SC | Buckenbowra | 531 | Non-scheduled | Unlicensed | Both | STS <50% | M | 86 | 2300 | 2017-09-07 | 2017-09-01 | 2017-09-14 |  |  | 2018-03-12 |  |  |  |  | 23 | 38 | 18 | 13 | 8 | 2 | 220 | 0 | 0 | 5 | 3 | No | 2 | 0
D | 126237 | SC | Termiel | 25 | Non-scheduled | Unlicensed | Both | STS <50% | H | 72 | 6950 | 2017-10-31 | 2017-11-01 | 2017-11-09 |  |  | 2018-03-01 |  |  |  |  | 55 | 42 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 3 | Yes | 1 | 0
D | 22285 | SC | Currowan | 217 | Non-scheduled | Unlicensed | Both | STS <50% | L | 200 | 2280 | 2017-11-27 | 2017-12-01 | 2017-12-10 |  |  | 2018-03-21 |  |  |  |  | 15 | 56 | 21 | 6 | 2 | 2 | 0 | 80 | 140 | 0 | 5 | No | 0 | 0
D | 22286 | SC | Currowan | 218 | Non-scheduled | Unlicensed | Both | STS <50% | L | 136 | 1490 | 2017-11-27 | 2017-12-01 | 2017-12-10 |  |  | 2018-03-21 |  |  |  |  | 23 | 51 | 15 | 8 | 3 | 2 | 0 | 105 | 0 | 0 | 1 | No | 0 | 0
D | 56202 | SC | Mogo | 137 | Non-scheduled | Unlicensed | Both | STS <50% | M | 53 | 1440 | 2017-01-09 | 2017-01-01 | 2017-01-10 | 2017-07-07 | 2018-02-01 | 2018-03-12 |  |  |  |  | 41 | 56 | 3 | 0 | 0 | 2 | 580 | 0 | 0 | 3 | 3 | Yes | 3 | 0
D | 56203 | SC | Mogo | 138 | Non-scheduled | Unlicensed | Both | STS <50% | M | 86 | 2320 | 2017-01-09 | 2017-01-01 | 2017-01-10 | 2017-07-07 | 2018-02-01 | 2018-03-12 |  |  |  |  | 36.7 | 57.1 | 5.9 | 0.3 | 0 | 2 | 350 | 0 | 0 | 2 | 1 | Yes | 2 | 0
D | 56204 | SC | Mogo | 139 | Non-scheduled | Unlicensed | Both | STS <50% | M | 181 | 4880 | 2017-01-09 | 2017-01-01 | 2017-01-10 | 2017-07-07 | 2018-02-01 | 2018-03-12 |  |  |  |  | 41 | 55 | 4 | 0.3 | 0 | 2 | 1230 | 0 | 0 | 1 | 4 | Yes | 1 | 0
D | 22284 | SC | Currowan | 219 | Non-scheduled | Unlicensed | Both | STS <50% | L | 205 | 2540 | 2017-02-06 | 2017-03-01 | 2017-11-02 |  |  | 2017-12-12 |  |  |  |  | 16 | 46 | 27 | 9 | 2 | 2 | 1480 | 290 | 140 | 4 | 4 | Yes | 2 | 0
D | 22303 | SC | Boyne | 107 | Non-scheduled | Unlicensed | Both | STS <50% | H | 417 | 14000 | 2016-07-11 | 2016-08-01 | 2016-08-01 |  |  | 2017-11-14 |  |  |  |  | 42 | 53 | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | Yes | 0 | 0
D | 56837 | SC | Mogo | 190 | Non-scheduled | Unlicensed | Both | STS <50% | H | 98 | 2230 | 2017-09-20 | 2017-09-01 | 2017-09-22 |  |  | 2017-11-06 |  |  |  |  | 54.7 | 43.8 | 1.3 | 0.1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 21942 | SC | Dampier | 3109 | Non-scheduled | Unlicensed | Both | STS <50% | H | 154.1 | 5500 | 2016-02-26 | 2016-09-01 | 2017-04-11 |  |  | 2017-10-13 |  |  |  |  | 6 | 21 | 26 | 33 | 14 | 2 | 0 | 0 | 0 | 0 | 1 | No | 0 | 0
D | 20659 | SC | Dampier | 3108 | Non-scheduled | Unlicensed | Both | STS <50% | M | 268 | 7333 | 2014-01-30 | 2014-02-01 | 2014-02-17 | 2014-05-30 | 2017-06-05 | 2017-10-13 | 2014-03-20 | 2014-05-30 | 2017-06-05 | 2017-10-13 | 4.1 | 24 | 27.8 | 30.1 | 14.1 | 2 | 400 | 510 | 1150 | 0 | 1 | Yes | 0 | 0
D | 56199 | SC | Boyne | 101 | Non-scheduled | Unlicensed | Both | STS <50% | M | 335 | 10100 | 2017-05-04 | 2017-05-04 | 2017-05-15 |  |  | 2017-10-25 |  |  |  |  | 45 | 49 | 4.5 | 0.6 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | No | 0 | 0
D | 126230 | SC | Mogo | 147 | Non-scheduled | Unlicensed | Both | STS <50% | H | 204 | 8530 | 2017-05-30 | 2017-06-01 | 2017-06-08 |  |  | 2017-10-03 |  |  |  |  | 35.1 | 60.5 | 3.9 | 0.4 | 0.1 | 2 | 82 | 0 | 0 | 0 | 1 | Yes | 1 | 0
D | 126231 | SC | Mogo | 148 | Non-scheduled | Unlicensed | Both | STS <50% | H | 101 | 5160 | 2017-05-30 | 2017-06-01 | 2017-06-08 |  |  | 2017-10-03 |  |  |  |  | 27.6 | 65.5 | 6.2 | 0.5 | 0.1 | 2 | 1621 | 50 | 0 | 0 | 1 | Yes | 0 | 0
D | 22296 | SC | North Brooman | 42 | Non-scheduled | Unlicensed | Both | STS <50% | H | 173.8 | 4875 | 2016-06-08 | 2016-09-01 | 2017-03-11 |  |  | 2017-09-08 |  |  |  |  | 28 | 56 | 12.9 | 2.9 | 0 | 2 | 0 | 66 | 0 | 0 | 4 | No | 0 | 0
D | 21984 | SC | Tallaganda | 2463 | Non-scheduled | Unlicensed | Both | STS <50% | M | 127 | 3800 | 2015-03-04 | 2017-02-01 | 2017-02-16 |  |  | 2017-07-20 |  |  |  |  | 52 | 46.5 | 1.4 | 0.1 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | Yes | 1 | 0
D | 21901 | SC | Tallaganda | 2461 | Non-scheduled | Unlicensed | Both | STS <50% | M | 72 | 1600 | 2015-01-15 | 2015-02-01 | 2017-05-23 |  |  | 2017-07-20 |  |  |  |  | 23 | 61.9 | 12.5 | 2.4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 22276 | SC | Mogo | 169 | Non-scheduled | Unlicensed | Both | STS <50% | L | 140 | 2200 | 2016-07-07 | 2016-09-01 | 2016-09-05 |  |  | 2017-03-10 |  |  |  |  | 26 | 63.8 | 8.8 | 0.7 | 0 | 2 | 660 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 22277 | SC | Mogo | 170 | Non-scheduled | Unlicensed | Both | STS <50% | L | 60 | 730 | 2016-07-07 | 2016-09-01 | 2016-09-05 |  |  | 2017-03-10 |  |  |  |  | 41 | 54 | 5 | 0.2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 22187 | SC | Wandera | 577 | Non-scheduled | Unlicensed | Both | STS <50% | L | 226 | 3660 | 2016-02-09 | 2016-09-01 | 2016-09-12 |  |  | 2017-02-22 |  |  |  |  | 11.1 | 49.9 | 25.6 | 8.7 | 4.7 | 2 | 2470 | 190 | 80 | 3 | 0 | No | 3 | 1
D | 22188 | SC | Wandera | 578 | Non-scheduled | Unlicensed | Both | STS <50% | L | 108.4 | 1464 | 2016-02-09 | 2016-09-01 | 2016-10-06 |  |  | 2017-02-22 |  |  |  |  | 10 | 37 | 26 | 18 | 9.2 | 2 | 370 | 140 | 80 | 1 | 1 | No | 1 | 0
D | 22256 | SC | North Brooman | 46 | Non-scheduled | Unlicensed | Both | STS <50% | H | 173 | 6214 | 2016-02-29 | 2016-03-01 | 2016-03-07 | 2016-08-15 | 2016-09-12 | 2017-01-13 |  |  |  |  | 44.8 | 48.9 | 4.3 | 1.4 | 0.7 | 2 | 0 | 0 | 0 | 0 | 3 | No | 0 | 0
D | 22257 | SC | North Brooman | 47 | Non-scheduled | Unlicensed | Both | STS <50% | H | 123 | 4170 | 2016-02-29 | 2016-03-01 | 2016-03-07 | 2016-08-15 | 2016-09-12 | 2017-01-13 |  |  |  |  | 36.2 | 37 | 11.6 | 9 | 6.3 | 2 | 0 | 0 | 0 | 0 | 3 | No | 0 | 0
D | 14450 | SC | Tallaganda | 2422 | Non-scheduled | Licensed | Both | STS <50% | M | 361 | 10300 | 2011-02-22 | 2014-01-01 | 2011-05-05 | 2012-08-31 | 2016-08-31 | 2016-11-11 | 2012-04-02 | 2012-08-31 | 2016-08-31 | 2016-11-11 | 52 | 38 | 9 | 1 | 0 | 1 | 1020 | 50 | 0 | 7 | 7 | Yes | Yes | 0
D | 20034 | SC | Termiel | 19 | Non-scheduled | Unlicensed | Both | STS <50% | H | 354.7 | 11600 | 2013-07-29 | 2014-01-01 | 2014-01-14 | 2015-04-22 | 2015-07-06 | 2015-11-19 |  |  |  |  | 66.1 | 29.9 | 3.7 | 0.3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | No | 0 | 0
D | 20035 | SC | Termiel | 20 | Non-scheduled | Licensed | Both | STS <50% | H | 151.5 | 10800 | 2013-07-29 | 2014-01-01 | 2014-01-14 | 2015-04-22 | 2015-07-06 | 2015-11-19 |  |  |  |  | 75.2 | 23.3 | 1.4 | 0.2 | 0 | 1 | 625 | 0 | 0 | 2 | 1 | No | 2 | 0
D | 22248 | SC | Flat Rock | 33 | Non-scheduled | Unlicensed | Both | STS <50% | M | 358.3 | 8630 | 2016-03-24 | 2016-03-01 | 2016-04-04 |  |  | 2016-09-05 |  |  |  |  | 47 | 50 | 3 | 0 | 0 | 2 | 690 | 50 | 0 | 0 | 0 | No | 0 | 0
D | 21961 | SC | Flat Rock | 36 | Non-scheduled | Unlicensed | Both | STS <50% | M | 230 | 1300 | 2015-04-20 | 2015-04-01 | 2015-08-31 | 2015-12-18 | 2016-08-15 | 2016-09-30 |  |  |  |  | 46 | 49 | 5 | 0 | 0 | 2 | 110 | 130 | 0 | 0 | 1 | Yes | 0 | 0
D | 20073 | SC | North Brooman | 43 | Non-scheduled | Unlicensed | Both | STS <50% | M | 197 | 6500 | 2013-06-13 | 2014-03-01 | 2014-03-03 |  |  | 2014-10-23 |  |  |  |  | 63 | 35 | 2 | 0 | 0 | 2 | 0 | 50 | 0 | 0 | 0 | Yes | 0 | 0
D | 21962 | SC | South Brooman | 48 | Non-scheduled | Unlicensed | Both | STS <50% | H | 115 | 8300 | 2015-03-04 | 2015-04-01 | 2015-04-27 |  |  | 2015-07-21 |  |  |  |  | 51 | 43 | 5.3 | 0.9 | 0.1 | 2 | 0 | 0 | 0 | 0 | 5 | Yes | 0 | 0
D | 20941 | SC | South Brooman | 51 | Non-scheduled | Unlicensed | Both | STS <50% | M | 249 | 6110 | 2014-10-08 | 2014-11-01 | 2014-11-06 |  |  | 2015-05-05 |  |  |  |  | 57 | 42 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 22258 | SC | South Brooman | 65 | Non-scheduled | Unlicensed | Both | STS <50% | H | 140 | 9400 | 2016-03-31 | 2016-04-01 | 2016-04-12 |  |  | 2016-08-01 |  |  |  |  | 52 | 42 | 5 | 1 | 0 | 2 | 0 | 140 | 30 | 2 | 2 | Yes | 1 | 0
D | 22237 | SC | South Brooman | 67 | Non-scheduled | Unlicensed | Both | STS <50% | M | 121.7 | 2860 | 2016-05-19 | 2016-06-01 | 2016-06-14 |  |  | 2016-10-05 |  |  |  |  | 65.2 | 31.2 | 4 | 0.1 | 0 | 2 | 0 | 60 | 0 | 0 | 0 | Yes | 0 | 0
D | 22029 | SC | Boyne | 95 | Non-scheduled | Unlicensed | Both | STS <50% | H | 222 | 6060 | 2015-10-21 | 2015-11-01 | 2015-11-06 |  |  | 2016-04-26 |  |  |  |  | 39 | 56 | 5 | 0 | 0 | 2 | 8400 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 20942 | SC | Boyne | 106 | Non-scheduled | Unlicensed | Both | STS <50% | M | 354.8 | 15250 | 2014-10-02 | 2014-10-01 | 2014-10-22 |  |  | 2015-11-11 |  |  |  |  | 62 | 37 | 1 | 0 | 0 | 2 | 47 | 145 | 0 | 0 | 1 | Yes | 1 | 0
D | 20847 | SC | Benandarah | 112 | Non-scheduled | Unlicensed | Both | STS <50% | H | 260 | 3616 | 2014-07-08 | 2014-06-01 | 2014-07-10 |  |  | 2015-01-20 |  |  |  |  | 56 | 41 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 20847 | SC | Benandarah | 113 | Non-scheduled | Unlicensed | Both | STS <50% | H | 260 | 3616 | 2014-07-08 | 2014-06-01 | 2014-07-10 |  |  | 2015-01-20 |  |  |  |  | 67 | 33 | 0 | 0 | 0 | 2 | 830 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 20763 | SC | Mogo | 162 | Non-scheduled | Unlicensed | Both | STS <50% | M | 110 | 4800 | 2014-04-16 | 2014-04-01 | 2014-04-23 |  |  | 2014-08-21 |  |  |  |  | 81 | 17.4 | 1.2 | 0.2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 20764 | SC | Mogo | 163 | Non-scheduled | Unlicensed | Both | STS <50% | M | 129 | 5480 | 2014-04-16 | 2014-04-01 | 2014-04-23 |  |  | 2014-08-21 |  |  |  |  | 67.4 | 31.6 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 22269 | SC | Mogo | 164 | Non-scheduled | Unlicensed | Both | STS <50% | H | 271 | 6010 | 2016-04-04 | 2016-04-01 | 2016-04-06 |  |  | 2016-09-06 |  |  |  |  | 52 | 43 | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 22182 | SC | Mogo | 186 | Non-scheduled | Unlicensed | Both | STS <50% | H | 194 | 9027 | 2015-09-29 | 2015-10-01 | 2015-10-06 |  |  | 2016-04-06 |  |  |  |  | 84 | 15 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2 | Yes | 1 | 0
D | 22126 | SC | Mogo | 187 | Non-scheduled | Unlicensed | Both | STS <50% | H | 114 | 7130 | 2015-07-02 | 2015-07-01 | 2015-07-06 |  |  | 2015-10-30 |  |  |  |  | 86.1 | 13.9 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | Yes | 1 | 0
D | 20856 | SC | Mogo | 189 | Non-scheduled | Licensed | Both | STS <50% | H | 187 | 10835 | 2014-07-10 | 2014-07-01 | 2014-07-30 |  |  | 2015-03-25 |  |  |  |  | 55.2 | 39.1 | 5.2 | 0.5 | 0 | 2 | 100 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 21848 | SC | Currowan | 227 | Non-scheduled | Unlicensed | Both | STS <50% | H | 187.6 | 2276 | 2014-10-02 | 2015-01-01 | 2015-01-20 |  |  | 2015-09-18 |  |  |  |  | 21 | 59.2 | 15.4 | 3.8 | 0.6 | 2 | 365 | 40 | 0 | 0 | 0 | Yes | 0 | 0
D | 21849 | SC | Currowan | 228 | Non-scheduled | Unlicensed | Both | STS <50% | H | 40.5 | 458 | 2014-10-02 | 2015-01-01 | 2015-01-20 |  |  | 2015-09-18 |  |  |  |  | 17.4 | 53.3 | 23.6 | 4.8 | 0.9 | 2 | 220 | 90 | 0 | 0 | 2 | Yes | 0 | 0
D | 20891 | SC | Currowan | 229 | Non-scheduled | Unlicensed | Both | STS <50% | H | 149.1 | 4300 | 2014-09-01 | 2014-12-01 | 2015-08-14 |  |  | 2016-03-09 |  |  |  |  | 23 | 61 | 13 | 3 | 0 | 2 | 90 | 40 | 0 | 0 | 1 | Yes | 0 | 0
D | 21850 | SC | Currowan | 230 | Non-scheduled | Unlicensed | Both | STS <50% | H | 29.3 | 685 | 2014-10-02 | 2015-01-01 | 2015-01-20 |  |  | 2015-09-18 |  |  |  |  | 17.4 | 51.4 | 20.1 | 8.7 | 2.3 | 2 | 0 | 0 | 0 | 0 | 1 | Yes | 0 | 0
D | 20798 | SC | Buckenbowra | 532 | Non-scheduled | Licensed | Both | STS <50% | M | 141 | 3600 | 2014-05-13 | 2014-05-01 | 2014-05-14 |  |  | 2014-07-29 | 2014-07-01 |  |  | 2014-07-21 | 47 | 46 | 6 | 1 |  | 2 | 320 | 0 | 0 | 0 | 7 | Yes | 0 | 0
D | 20169 | SC | Wandera | 568 | Non-scheduled | Unlicensed | Both | STS <50% | M | 150 | 2810 | 2014-04-07 | 2014-04-01 | 2014-04-28 |  |  | 2014-07-25 |  |  |  |  | 16.6 | 42 | 24 | 14 | 3 | 2 | 200 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 20170 | SC | Wandera | 569 | Non-scheduled | Unlicensed | Both | STS <50% | M | 128 | 2370 | 2014-04-07 | 2014-04-01 | 2014-04-28 |  |  | 2014-07-25 |  |  |  |  | 5.5 | 26 | 25 | 18.7 | 3.7 | 2 | 200 | 0 | 40 | 0 | 0 | No | 0 | 0
D | 20168 | SC | Mogo | 570 | Non-scheduled | Unlicensed | Both | STS <50% | M | 64 | 1200 | 2014-04-07 | 2014-04-01 | 2014-04-28 |  |  | 2014-07-25 |  |  |  |  | 6 | 29 | 25 | 18.7 | 20.6 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 20166 | SC | Mogo | 575 | Non-scheduled | Licensed | Both | STS <50% | L | 62 | 900 | 2013-07-29 | 2013-08-01 | 2013-08-08 |  |  | 2014-07-09 | 2013-08-08 |  |  | 2014-07-09 | 5.4 | 26.4 | 31.1 | 26.6 | 10.5 | 2 | 400 | 0 | 0 | 0 | 0 | No | 0 | 0
D | 20167 | SC | Wandera | 576 | Non-scheduled | Licensed | Both | STS <50% | L | 213 | 3100 | 2013-07-29 | 2013-08-01 | 2013-08-08 |  |  | 2014-07-09 | 2013-08-08 |  |  | 2014-07-09 | 10 | 38 | 25 | 18 | 9 | 2 | 2030 | 50 | 400 | 1 | 3 | No | 1 | 0
D | 21909 | SC | Wandera | 582 | Non-scheduled | Unlicensed | Both | STS <50% | L | 81 | 880 | 2015-03-06 | 2015-03-01 | 2015-03-24 | 2015-04-28 | 2016-07-18 | 2016-09-13 |  |  |  |  | 9 | 39 | 25 | 19 | 8 | 2 | 330 | 200 | 0 | 0 | 0 | No | 0 | 0
D | 21910 | SC | Wandera | 583 | Non-scheduled | Unlicensed | Both | STS <50% | L | 138 | 2400 | 2015-03-06 | 2015-03-01 | 2015-03-24 | 2015-04-28 | 2016-07-18 | 2016-09-13 |  |  |  |  | 15 | 45 | 21 | 12 | 7 | 2 | 0 | 80 | 0 | 0 | 0 | No | 0 | 0
D | 20599 | SC | Tallaganda | 2413 | Non-scheduled | Licensed | Both | STS <50% | H | 125 | 12300 | 2014-01-21 | 2014-02-01 | 2014-06-08 |  |  | 2014-09-29 |  |  |  |  | 11.9 | 57.9 | 15.4 | 8.3 | 6.4 | 1 | 470 | 0 | 0 | 0 | 0 | Yes | 0 | 0
D | 531 | SC | Tallaganda | 2416 | Non-scheduled | Licensed | Both | STS <50% | H | 416.5 | 27600 | 2009-04-16 | 2014-02-01 | 2009-04-28 | 2011-04-22 | 2014-02-17 | 2014-07-10 | 2010-10-19 |  |  | 2014-07-10 | 21 | 52 | 18 | 8 | 1 | 1 | 610 | 0 | 0 | 0 | 4 | Yes | 2 | 0
D | 10881 | SC | Tallaganda | 2418 | Non-scheduled | Unlicensed | Both | STS <50% | M | 205 | 1700 | 2003-04-26 | 2015-04-01 | 2004-09-27 | 2007-08-24 | 2015-04-08 | 2015-09-02 |  |  |  |  | 35 | 51 | 10 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | No | 0 | 0
D | 20260 | SC | Tallaganda | 2445 | Non-scheduled | Unlicensed | Both | STS <50% | H | 286 | 20000 | 2013-08-29 | 2014-09-01 | 2013-10-04 | 2014-02-28 | 2014-10-03 | 2014-11-07 |  |  |  |  | 21.4 | 48 | 15 | 10 | 6 | 1 | 260 | 50 | 0 | 3 | 14 | Yes | 0 | 3
D | 22168 | SC | Tallaganda | 2489 | Non-scheduled | Unlicensed | Both | STS <50% | M | 170 | 5930 | 2011-06-10 | 2015-08-01 | 2015-09-02 | 2015-10-20 | 2016-06-17 | 2016-09-02 |  |  |  |  | 54.2 | 36.5 | 0.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | Yes | 0 | 0
D | 20600 | SC | Bodalla | 3010 | Non-scheduled | Unlicensed | Both | STS <50% | M | 139.5 | 3245 | 2014-08-14 | 2014-09-01 | 2014-09-15 |  |  | 2014-11-10 |  |  |  |  | 94.3 | 5.3 | 0.3 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | No | 3 | 0
D | 20918 | SC | Bodalla | 3011 | Non-scheduled | Unlicensed | Both | STS <50% | M | 14.3 | 350 | 2014-08-14 | 2014-09-01 | 2014-09-15 |  |  | 2014-11-10 |  |  |  |  | 75.4 | 19.8 | 1.9 | 1.4 | 1.5 | 2 | 0 | 0 | 0 | 0 | 1 | No | 0 | 0
D | 22067 | SC | Bodalla | 3027 | Non-scheduled | Unlicensed | Both | STS <50% | M | 160 | 3019 | 2015-10-26 | 2016-01-01 | 2016-01-08 |  |  | 2016-03-08 |  |  |  |  | 36.6 | 56.2 | 5.3 | 1.7 | 0.2 | 2 | 80 | 60 | 0 | 3 | 1 | Yes | 0 | 3
D | 56200 | SC | Yadboro | 446 | Non-scheduled | Unlicensed | Both | STS <50% | L | 277 | 3145 | 2012-04-24 | 2016-10-04 | 2016-10-04 |  |  | 2017-04-13 |  |  |  |  | 15 | 40 | 26 | 14 | 5 | 2 | 960 | 30 | 150 | 0 | 0 | No | 0 | 0
F | 64205 | SC | Clyde | 206 | Non-scheduled | Unlicensed | Both | STS <50% | M | 151 | 4680 | 2011-06-10: 2018-05-28; 2015-08-01: 2018-05-01 |  |  |  |  | 15 | 47 | 25 | 10 | 3 | 2 | 400 | 0 | 100 | 0 | 1 | No | 0 | 0
F | 64206 | SC | Clyde | 467 | Non-scheduled | Unlicensed | Both | STS <50% | M | 81 | 2200 | 2011-06-10: 2018-05-28; 2015-08-01: 2018-05-01 |  |  |  |  | 18 | 40 | 26 | 13 | 3 | 2 | 400 | 0 | 0 | 0 | 0 | No | 0 | 0
F | 126347 | SC | Badja | 2019 | Non-scheduled | Unlicensed | Both | STS <50% | H | 195 | 9650 | 2011-06-10: 2018-05-17; 2015-08-01: 2018-04-01 |  |  |  |  | 39 | 51 | 8 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 3 | No | 1 | 1
F | 126348 | SC | Flat Rock | 31 | Non-scheduled | Unlicensed | Both | STS <50% | H | 365 | 4175 | 2011-06-10: 2018-05-17; 2015-08-01: 2018-05-01 |  |  |  |  | 56 | 39 | 4 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
F | 126349 | SC | Flat Rock | 32 | Non-scheduled | Unlicensed | Both | STS <50% | H | 367 | 6700 | 2011-06-10: 2018-05-17; 2015-08-01: 2018-05-01 |  |  |  |  | 36 | 56 | 7 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
F | 20066 | SC | Currambene | 1039 | Non-scheduled | Unlicensed | Both | STS <50% | H | 61.6 | 6000 | 2011-06-10: 2013-01-18; 2015-08-01: 2014-10-01 |  |  |  |  | 100 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
F | 20067 | SC | Currambene | 1040 | Non-scheduled | Unlicensed | Both | STS <50% | H | 173.6 | 17000 | 2011-06-10: 2013-01-18; 2015-08-01: 2014-10-01 |  |  |  |  | 100 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
F | 20731 | SC | Tomerong | 1199 | Non-scheduled | Unlicensed | Both | STS <50% | M | 91.7 | 2000 | 2011-06-10: 2014-03-25; 2015-08-01: 2014-07-01 |  |  |  |  | 97.7 | 2.3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | Yes | 0 | 0
F | 64213 | SC | Dampier | 3131 | Non-scheduled | Unlicensed | Both | STS <50% | L | 0 | 0 | 2011-06-10: 2017-05-24; 2015-08-01: 2017-07-01 |  |  |  |  | 11 | 42 | 25 | 17 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
F | 64214 | SC | Dampier | 3132 | Non-scheduled | Unlicensed | Both | STS <50% | L | 219 | 3450 | 2011-06-10: 2017-05-24; 2015-08-01: 2017-07-01 |  |  |  |  | 10 | 37 | 29 | 19 | 5 | 2 | 600 | 1100 | 150 | 0 | 0 | No | 0 | 0
F | 64215 | SC | Dampier | 3133 | Non-scheduled | Unlicensed | Both | STS <50% | L | 304 | 3000 | 2011-06-10: 2017-05-24; 2015-08-01: 2017-07-01 |  |  |  |  | 12 | 44 | 26 | 15 | 3 | 2 | 0 | 0 | 100 | 0 | 0 | No | 0 | 0
F | 64202 | SC | Dampier | 3123 | Non-scheduled | Unlicensed | Both | STS <50% | M | 102 | 3000 | 2011-06-10: DRAFT; 2015-08-01: 2017-09-01 |  |  |  |  | 4 | 25 | 41 | 24 | 6 | 2 | 0 | 0 | 340 | 0 | 0 | No | 0 | 0
F | 64203 | SC | Dampier | 3127 | Non-scheduled | Unlicensed | Both | STS <50% | H | 70 | 3300 | 2011-06-10: DRAFT; 2015-08-01: 2017-09-01 |  |  |  |  | 5 | 23 | 36 | 30 | 6 | 2 | 0 | 60 | 155 | 0 | 1 | No | 0 | 0
F | 64204 | SC | Dampier | 3128 | Non-scheduled | Unlicensed | Both | STS <50% | M | 92 | 3800 | 2011-06-10: DRAFT; 2015-08-01: 2017-09-01 |  |  |  |  | 5 | 27 | 39 | 28 | 1 | 2 | 485 | 160 | 250 | 0 | 0 | No | 0 | 0
S | 12774 | SC | Buckenbowra | 517 | Non-scheduled | Unlicensed | Both | STS <50% | M | 294 | 7350 | 2017-02-06 | 2017-02-01 | 2017-02-13 | 2017-02-25 | [6 empty] | 11 | 47 | 26 | 16 | 0 | 2 | 0 | 60 | 100 | 0 | 1 | No | 0 | 0
S | 20045 | SC | Yadboro | 407 | Non-scheduled | Licensed | Both | STS <50% | H | 217.7 | 5685 | 2017-04-12 | 2017-04-03 | 2017-04-14 | 2017-05-12 | [6 empty] | 10 | 63.3 | 22.85 | 3.5 | 0 | 2 | 245 | 0 | 0 | 0 | 0 | No | 0 | 0
S | 22218 | SC | Bolaro | 245 | Non-scheduled | Unlicensed | Both | STS <50% | H | 205 | 5490 | 2016-02-01 | 2016-03-01 | 2016-02-26 | 2016-04-22 | [6 empty] | 28 | 53 | 14 | 3 | 2 | 2 | 200 | 200 | 0 | 0 | 0 | No | 0 | 0
S | 20065 | SC | Currambene | 1038 | Non-scheduled | Unlicensed | Both | STS <50% | H | 20.3 | 2000 | 2013-01-18 | 2013-10-01 | 2013-04-02 | 2013-05-31 | [6 empty] | 99.2 | 0.8 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
S | 20068 | SC | Currambene | 1041 | Non-scheduled | Unlicensed | Both | STS <50% | L | 147.6 | 1450 | 2013-01-18 | 2013-10-01 | 2013-04-15 | 2013-05-31 | [6 empty] | 100 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Yes | 0 | 0
S | 20069 | SC | Currambene | 1042 | Non-scheduled | Unlicensed | Both | STS <50% | H | 82.2 | 8000 | 2013-01-18 | 2013-01-01 | 2013-01-23 | 2013-05-31 | [6 empty] | 37.3 | 62.7 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | Yes | 0 | 0
S | 14610 | SC | Yerriyong | 1153 | Non-scheduled | Licensed | Both | STS <50% | M | 239 | 4553 | 2015-01-13 | 2015-04-01 | 2011-10-24 | 2015-04-06 |  |  | 2011-10-24 | 2015-04-06 |  |  | 14 | 46 | 27 | 10 | 3 | 3 | 0 | 50 | 0 | 0 | 1 | No | 0 | 0
S | 14611 | SC | Yerriyong | 1156 | Non-scheduled | Unlicensed | Both | STS <50% | M | 99 | 2380 | 2015-01-13 | 2015-01-01 | 2012-02-06 | 2015-04-06 | [6 empty] | 16 | 44 | 24 | 13 | 3 | 2 | 0 | 0 | 0 | 0 | 3 | Yes | 0 | 0
S | 22062 | SC | Badja | 2029 | Non-scheduled | Licensed | Both | STS <50% | H | 37.1 | 1676 | 2015-05-01 | 2015-05-01 | 2015-05-05 | 2016-06-17 |  |  | 2015-05-05 | 2016-06-17 |  |  | 33.8 | 51.8 | 10.3 | 2.5 | 1.5 | 2 | 300 | 80 | 0 | 0 | 1 | No | 0 | 0
S | 22063 | SC | Badja | 2031 | Non-scheduled | Licensed | Both | STS <50% | H | 135.8 | 6146 | 2015-05-01 | 2015-05-01 | 2015-05-05 | 2016-06-17 |  |  | 2015-05-05 | 2016-06-17 |  |  | 29.5 | 47.3 | 12.1 | 6.1 | 5.1 | 2 | 1935 | 200 | 0 | 1 | 0 | No | 1 | 0
S | 22078 | SC | Badja | 2045 | Non-scheduled | Licensed | Roading |  |  |  |  | 2015-05-01 | 2015-05-01 | 2015-05-05 | 2016-06-17 |  |  | 2015-05-05 | 2016-06-17 |  |  | 43.7 | 48.2 | 6 | 1.5 | 0.6 | 2 | 370 | 0 | 0 | 0 | 0 | No | 0 | 0
S | 22079 | SC | Badja | 2046 | Non-scheduled | Licensed | Roading |  |  |  |  | 2015-05-01 | 2015-06-01 | 2015-06-01 | 2016-06-17 |  |  | 2015-06-01 | 2016-06-17 |  |  | 48 | 41 | 8 | 3 | 0 | 2 | 450 | 100 | 0 | 0 | 0 | No | 0 | 0
S | 14309 | SC | Badja | 2086 | Non-scheduled | Unlicensed | Both | STS <50% | L | 172 | 2752 | 2010-08-30 | 2013-06-01 | 2012-02-16 | 2012-03-31 | [6 empty] | 83.8 | 16 | 0.2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | No | 0 | 0
S | 20633 | SC | Tallaganda | 2457 | Non-scheduled | Unlicensed | Both | STS <50% | M | 201 | 5600 | 2014-10-07 | 2014-10-01 | 2014-11-07 | 2014-12-31 | [6 empty] | 21.9 | 53.3 | 17.7 | 6 | 1.1 | 1 | 0 | 100 | 0 | 0 | 3 | Yes | 0 | 0
S | 14809 | SC | Bodalla | 3064 | Non-scheduled | Licensed | Both | STS <50% | L | 357 | 5609 | 2012-05-23 | 2014-01-01 | 2012-05-25 | 2012-10-20 |  |  | 2012-06-19 | 2012-10-20 |  |  | 13.8 | 50 | 25.8 | 8.3 | 2.1 | 2 | 0 | 20 | 0 | 0 | 0 | No | 0 | 0
|  | SC | Bodalla | 3022 | Non-scheduled | Unlicensed | Both | STS <50% |  |  |  | 2015-08-01: 2018-04-01
|  | SC | Bodalla | 3004 | Non-scheduled | Unlicensed | Both | STS <50% |  |  |  | 2015-08-01: 2018-04-01
|  | SC | Corunna | 3058 | Non-scheduled | Unlicensed | Both | STS <50% |  |  |  | 2015-08-01: 2018-04-01